{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":30,"n_cols":30,"rows_kept":30,"merged":[[3,6,3,29],[4,7,4,14],[4,15,4,21],[4,22,4,25],[4,26,4,28]],"flags":["formulas_cached_only"]}
[]
[]
[]
[{"$nulls":6},"XXXX设计项目时间进度控制甘特图"]
[{"$nulls":6},"10月","2015-11-01",{"$nulls":7},"2015-12-01",{"$nulls":6},"2016-01-01",{"$nulls":3},"2016-02-01",null,null,"2016年3月--5月"]
[{"$nulls":6},31,1,2,3,4,5,6,7,"8--31","1--9",10,11,12,13,14,"15--31","1--15",16,17,"18--30","1--18","19--24","25--31","3月--5月"]
[{"$nulls":15},"市场调研与分析"]
[{"$nulls":14},"前期概念设计"]
[{"$nulls":15},"设计研讨会"]
[{"$nulls":16},"设计方案制作"]
[{"$nulls":18},"设计方案评审"]
[{"$nulls":19},"设计方案汇报"]
[{"$nulls":21},"设计研讨会"]
[{"$nulls":23},"设计方案整合与深化"]
[{"$nulls":23},"项目展示影视及多媒体策划、拍摄、剪辑、制作"]
[{"$nulls":23},"与项目提供方密切沟通协调"]
[{"$nulls":24},"最终设计方案向项目提供方汇报"]
[{"$nulls":25},"第三次设计研讨会"]
[{"$nulls":28},"展览模型及物料制作"]
[]
[{"$nulls":26},"       ",null,"展览准备及布展"]
{"$rows_empty":8}
[{"$nulls":28}," "]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}